## Sheet1
Schedule PCB Improvement
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24
|  |  |  | 22-26 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan
actual
3 | Design system | Supakorn | plan
actual
4 | Start develop system | Supakorn | plan
actual
5 | Layout setting support new operation | Arnon | plan
actual
6 | Equipment support | Surasak | plan
actual
7 | Trail test | Store PCB/IT member | plan
actual
8 | Start use New system | Store PCB/IT member | plan
actual
9 | Follow up & action problem | Store PCB/IT member | plan
actual
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24
|  |  |  | 22-26 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan
actual
3 | Design system | Supakorn | plan
actual
4 | Start develop system | Supakorn | plan
actual
5 | Layout setting support new operation | Arnon | plan
actual
6 | Equipment support | Surasak | plan
actual
7 | Trail test | Store PCB/IT member | plan
actual
8 | Start use New system | Store PCB/IT member | plan
actual
9 | Follow up & action problem | Store PCB/IT member | plan
actual
Schedule PCB Improvement IT
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24 |  |  |  | Status | date
|  |  |  | 22-26 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan | [6 empty] | Equipment support | [7 empty] | Complate | 2024-01-26
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan
actual
3 | Design system | Supakorn | plan
actual
| -User interface design | User | plan
| -system flow | Supakorn | plan
| -Structure DB |  | plan
| -IT working grop flow "start dev" | Supakorn/Surasak/ICS | plan
4 | Start develop system | Supakorn | plan
actual
| -Combine system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
| -Strategy system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
7 | Trail test | Store PCB/IT member | plan
actual
| -debug testing | Store PCB/Supakorn | plan
| -User manual system |  | plan
| -Traning users |  | plan
8 | Start use New system | Store PCB/IT member | plan
actual
| -IT working grop flow "Golive" | Supakorn/Nattapong/ICS | plan
9 | Follow up & action problem | Store PCB/IT member | plan
actual

## Sheet2
Schedule PCB improvement IT |  |  |  | Rev 26/01/2024
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24 |  |  |  | Status | date | Confrim | REMARK
|  |  |  | 22-26 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan | [14 empty] | Complate | 2024-01-26 | suprakorn
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan | [17 empty] | detail get requirement / concept
actual
| -Get detail Combine and Strategy | Store PCB/IT member | plan
3 | Design system | Supakorn | plan
actual
| -User interface design | User | plan
| -system flow | Supakorn | plan
| -Structure DB |  | plan
| -IT working grop flow "start dev" | Supakorn/Surasak/ICS | plan
| -Infrom manager | Supakorn | plan
4 | Start develop system | Supakorn | plan
actual
| -Combine system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
| -Strategy system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
7 | Trail test | Store PCB/IT member | plan
actual
| -debug testing | Store PCB/Supakorn | plan
| -User manual system |  | plan
| -Traning users |  | plan
8 | Start use New system | Store PCB/IT member | plan
actual
| -IT working grop flow "Golive" | Supakorn/Nattapong/ICS | plan
9 | Follow up & action problem | Store PCB/IT member | plan
actual
| Plan-Major |  | Plan-minor |  | actual |  | Waiting for information |  |  | Not in IT process |  |  | delay
8/01/2024

## plan06022024
Schedule PCB improvement IT |  |  |  | Rev 26/01/2024
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24 |  |  |  | Status | date | Confrim | REMARK
|  |  |  | w4 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan | [14 empty] | Complate | 2024-01-26 | suprakorn
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan
actual
| -Get detail Combine and Strategy | Store PCB/IT member | plan
3 | Design system | Supakorn | plan
actual
| -User interface design | User | plan
| -system flow | Supakorn | plan
| -Structure DB |  | plan
| -IT working grop flow "start dev" | Supakorn/Surasak/ICS | plan
| -Infrom manager | Supakorn | plan
4 | Start develop system | Supakorn | plan
actual
| -Combine system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
| -Strategy system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
7 | Trail test | Store PCB/IT member | plan
actual
| -debug testing | Store PCB/Supakorn | plan
| -User manual system |  | plan
| -Traning users |  | plan
8 | Start use New system | Store PCB/IT member | plan
actual
| -IT working grop flow "Golive" | Supakorn/Nattapong/ICS | plan
9 | Follow up & action problem | Store PCB/IT member | plan
actual
| Plan-Major |  | Plan-minor |  | actual |  | Waiting for information |  |  | Not in IT process |  |  | delay
8/01/2024

## plan13022024
Schedule PCB improvement IT |  |  |  | Rev 26/01/2024
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24 |  |  |  | Status | date | Confrim | REMARK
|  |  |  | w4 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan | [14 empty] | Complate | 2024-01-26 | suprakorn
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan
actual
| -Get detail Combine and Strategy | Store PCB/IT member | plan
3 | Design system | Supakorn | plan | [17 empty] | แก้โปรแกรมที่มีปัญหา
actual
| -User interface design | User | plan | [17 empty] | user ไม่มี desige IT ไปถามเอง
| -system flow | Supakorn | plan
| -Structure DB |  | plan
| -IT working grop flow "start dev" | Supakorn/Surasak/ICS | plan
| -Infrom manager | Supakorn | plan
4 | Start develop system | Supakorn | plan
actual
| -Combine system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
| -Strategy system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
7 | Trail test | Store PCB/IT member | plan
actual
| -debug testing | Store PCB/Supakorn | plan
| -User manual system |  | plan
| -Traning users |  | plan
8 | Start use New system | Store PCB/IT member | plan
actual
| -IT working grop flow "Golive" | Supakorn/Nattapong/ICS | plan
9 | Follow up & action problem | Store PCB/IT member | plan
actual
| Plan-Major |  | Plan-minor |  | actual |  | Waiting for information | [5 empty] | delay
13/01/2024

## plan16022024
Schedule PCB improvement IT |  |  |  | Rev 26/01/2024
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24 |  |  |  | Status | date | Confrim | REMARK
|  |  |  | w4 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan | [14 empty] | Complate | 2024-01-26 | suprakorn
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan
actual
| -Get detail Combine and Strategy | Store PCB/IT member | plan
2.1 | แก้ไขโปรแกรมเก่าที่มีปัญหา | Supakorn | plan
| -Combine | Supakorn | actual
| -Strategy | Supakorn | actual
| -Daily stock | Supakorn | actual
3 | Design system | Supakorn | plan | [17 empty] | แก้โปรแกรมที่มีปัญหา
actual
| -User interface design | User | plan
| -system flow | Supakorn | plan
| -Structure DB |  | plan
| -IT working grop flow "start dev" | Supakorn/Surasak/ICS | plan
| -Infrom manager | Supakorn | plan
4 | Start develop system | Supakorn | plan
actual
| -Combine system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
| -Strategy system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
7 | Trail test | Store PCB/IT member | plan
actual
| -debug testing | Store PCB/Supakorn | plan
| -User manual system |  | plan
| -Traning users |  | plan
8 | Start use New system | Store PCB/IT member | plan
actual
| -IT working grop flow "Golive" | Supakorn/Nattapong/ICS | plan
9 | Follow up & action problem | Store PCB/IT member | plan
actual
| Plan-Major |  | Plan-minor |  | actual |  | Waiting for information | [5 empty] | delay
13/01/2024

## plan23022024
Schedule PCB improvement IT |  |  |  | Rev 26/01/2024
No | Detail | P.I.C |  | Jan’24 |  | Feb’24 |  |  |  | Mar’24 |  |  |  | Apr’24 |  |  |  | Status | date | Confrim | REMARK
|  |  |  | w4 | 29-31 | 5-9 | 12-16 | 19-23 | 26-29 | 4-9 | 11-15 | 18-22 | 25-29 | 1-5 | 8-11 | 18-20 | 22-26
1 | Issue concept idea | Surasak / Supakorn | plan | [14 empty] | Complate | 2024-01-26 | suprakorn
actual
2 | Confirm detail get requirement / concept | Store PCB/IT member | plan
actual
| -Get detail Combine and Strategy | Store PCB/IT member | plan
2.1 | แก้ไขโปรแกรมเก่าที่มีปัญหา | Supakorn | plan
| -Strategy | Supakorn | actual
| -Combine | Supakorn | actual | [17 empty] | Start22-02-2024 Delay REPLACE PC 17 UNIT AUDIT WIRELES 75 UINT Reprint 3 UNIT
| -Daily stock | Supakorn | actual
3 | Design system | Supakorn | plan | [17 empty] | แก้โปรแกรมที่มีปัญหา
actual
| -User interface design | User | plan
| -system flow | Supakorn | plan
| -Structure DB |  | plan
| -IT working grop flow "start dev" | Supakorn/Surasak/ICS | plan
| -Infrom manager | Supakorn | plan
4 | Start develop system | Supakorn | plan
actual
| -Combine system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
| -Strategy system(Calling parts) |  | plan
| -update detail after get requirement / concept |  | plan
7 | Trail test | Store PCB/IT member | plan
actual
| -debug testing | Store PCB/Supakorn | plan
| -User manual system |  | plan
| -Traning users |  | plan
8 | Start use New system | Store PCB/IT member | plan
actual
| -IT working grop flow "Golive" | Supakorn/Nattapong/ICS | plan
9 | Follow up & action problem | Store PCB/IT member | plan
actual
| Plan-Major |  | Plan-minor |  | actual |  | Waiting for information | [5 empty] | delay
23/01/2024